## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
No1 | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
1 | Login with Google | Login with Google | Simple | Iteration 1 | SE140380 | Nguyễn Hữu Huy | Iteration 1
2 | Get schedule | View Schedule | Simple | Iteration 1 | SE140380 | Nguyễn Hữu Huy | Iteration 1
3 | Get own profile | View Profile | Simple | Iteration 2 | SE140380 | Nguyễn Hữu Huy | Iteration 1
4 | Edit own profile | View Profile | Simple | Iteration 2 | SE140380 | Nguyễn Hữu Huy | Iteration 1
5 | Disable subjects | View Profile | Simple | Iteration 2 | SE140380 | Nguyễn Hữu Huy | Iteration 1
6 | Search mentor by name | Search Mentor | Medium | Iteration 2 | SE140380 | Nguyễn Hữu Huy | Iteration 1
7 | Search mentor by subject | Search Mentor | Medium | Iteration 3 | SE140380 | Nguyễn Hữu Huy | Iteration 2
8 | Get mentor profile and available slot | View Mentor profile and available slot | Simple | Iteration 3 | SE140380 | Nguyễn Hữu Huy | Iteration 1
9 | Get slot detail | View slot in detail | Simple | Iteration 1 | SE140682 | Vũ Quốc Hùng | Iteration 1
10 | Add question | Booking | Simple | Iteration 1 | SE140683 | Vũ Quốc Hùng | Iteration 1
11 | Send booking request | Booking | Simple | Iteration 2 | SE140684 | Vũ Quốc Hùng | Iteration 1
12 | Get booking requests | View Booking Requests | Simple | Iteration 2 | SE140685 | Vũ Quốc Hùng | Iteration 1
13 | Get booking request details | View Booking Request Detail | Simple | Iteration 2 | SE140380 | Vũ Quốc Hùng | Iteration 1
14 | Accept request | View Booking Request Detail | Simple | Iteration 3 | SE140686 | Vũ Quốc Hùng | Iteration 1
15 | Deny request | View Booking Request Detail | Simple | Iteration 3 | SE140687 | Vũ Quốc Hùng | Iteration 1
16 | Create available slot | Create available slot | Simple | Iteration 1 | SE140742 | Nguyễn Nhựt Hào | Iteration 1
17 | Update available slot | Update available slot | Simple | Iteration 1 | SE140742 | Nguyễn Nhựt Hào | Iteration 1
18 | Remove available slot | Remove available slot | Simple | Iteration 2 | SE140742 | Nguyễn Nhựt Hào | Iteration 1
19 | Register mentor | Register mentor | Simple | Iteration 2 | SE140742 | Nguyễn Nhựt Hào | Iteration 1
20 | Register subjects | Register subjects | Simple | Iteration 2 | SE140742 | Nguyễn Nhựt Hào | Iteration 1
21 | Login with system account | Login with system account | Simple | Iteration 3 | SE140742 | Nguyễn Nhựt Hào | Iteration 1
22 | Get all statistic | View statistic | Medium | Iteration 3 | SE140742 | Nguyễn Nhựt Hào | Iteration 1
23 | Get all requests | View all requests | Simple | Iteration 3 | SE140742 | Nguyễn Thế Nhân | Iteration 1
24 | Get request detail | View request detail | Simple | Iteration 1 | SE140758 | Nguyễn Thế Nhân | Iteration 1
25 | Get all accounts | View all accounts | Simple | Iteration 1 | SE140758 | Nguyễn Thế Nhân | Iteration 1
26 | Get account detail | View account detail | Simple | Iteration 2 | SE140758 | Nguyễn Thế Nhân | Iteration 1
27 | Get all subjects | View all subjects | Simple | Iteration 2 | SE140758 | Nguyễn Thế Nhân | Iteration 1
28 | Create subject | Create new subject | Simple | Iteration 3 | SE140758 | Nguyễn Thế Nhân | Iteration 1
29 | Edit subject | Edit subject | Simple | Iteration 3 | SE140758 | Nguyễn Thế Nhân | Iteration 1
30 | Answer question | Mentor | Simple | Iteration 2 | SE140380 | Nguyễn Hữu Huy | Iteration 1
31 | View question | Mentor | Simple | Iteration 2 | SE140682 | Vũ Quốc Hùng | Iteration 1
32 | Get all major | Major | Simple | Iteration 2 | SE140380 | Vũ Quốc Hùng | Iteration 1
33 | Add major | Create Major | Simple | Iteration 2 | SE140380 | Nguyễn Nhựt Hào | Iteration 1
34 | Delete major | Edit Major | Simple | Iteration 2 | SE140380 | Nguyễn Thế Nhân | Iteration 1
35 | Edit major | Edit Major | Simple | Iteration 2 | SE140380 | Nguyễn Thế Nhân | Iteration 1
36 | Rating and comment | History Details | Medium | Iteration 2 | SE140380 | Nguyễn Nhựt Hào | Iteration 1