## Week 01
PROJECT REPORT
Group | Group 01 - Mentor Appointment Scheduling Application
Week | 09/05/2022 - 14/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Setup Project | In Progress | Set up code, GitHub, Azure, Drive, Document
2 | Write I section in SRS Document | In Progress
3 | Analyze Requirement | In Progress | Make clarity the requirements
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Draw Context Diagram, Draw Screen Flow of user (Mentor & Student) | HungVQ
2 | Setup Drive, Create GitHub repository | HuyNH
3 | Setup Code Backend in GitHub repository, write Introduction in Overview, write Weekly report | HaoNN
4 | Draw Screen Flow of Admin | NhanNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Define bussiness | Completed
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Draw ERD | 2022-05-18 | Prepare ERD for setup DB, use for code describe the DB with CodeFirst
2 | Design Database | 2022-05-20
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A | N/A | N/A | N/A

## Week 02
PROJECT REPORT
Group | Group 01 - Mentor Appointment Scheduling Application
Week | 16/05/2022 - 20/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Design Database, Implement in local, and Azure | In Progress
2 | Write document I Section in SRS, design ERD | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design ERD, Database | All members
2 | Implement DB in local and Azure, Prepare Week02 report | HaoNN
3 | Fix document , section 1, define product backlog | HuyNH, HungVQ, NhanNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
N/A | N/A | Completed | N/A
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start coding functions in backend. | 2022-05-27 | Set up base
2 | Start coding in font-end | 2022-05-27 | Set up base
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A | N/A | N/A | N/A

## Week 03
PROJECT REPORT
Group | Group 01 - Mentor Appointment Scheduling Application
Week | 23/05/2022 - 27/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Start coding in backend. | Completed | Setup base infrastructure for code
2 | Start coding in font-end. | Completed | Setup base infrastructure for code
3 | Draw Wireframe for font-ent UI | In Progress
4 | Modified producti backlog | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Implement Database with Code first approach | HaoNN
2 | Implement Subject Function (5 APIs) in Backend | HaoNN
3 | Implement Test Sybject Function Unit Test & Automated Test | HaoNN | (Unit test in Core layer)
4 | Implement Major Function (5 APIs) in Backend | NhanNT
5 | Implement Test MajorFunction Unit Test & Automated Test | NhanNT
6 | Implement manage subjects on Frontend | HungVQ
7 | Implement manage major on Frontend | HungVQ
8 | Fix overall diagram for SRS document | HungVQ
9 | Add more feature for SRS document | HungVQ
10 | Add more feature for Product backlog document | HungVQ
8 | Create UI for login web admin | HuyNH
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
N/A | N/A | In Progress | N/A
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Modify DB: add Major, add Rating for Mentor base on each Appointment
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A | N/A | N/A | N/A

## Week 04
PROJECT REPORT
Group | Group 01 - Mentor Appointment Scheduling Application
Week | 30/05/2022 - 03/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Modify DB: add Major, add Rating for Mentor base on each Appointment | Completed
2 | Coding backend and font end | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Modify DB: add Major, add Rating for Mentor base on each Appointment | HaoNN
2 | Add Intergration test for Infrastructure | HaoNN | Setup in local and in GitHub Actions
3 | Add MentorSubjects Functions (4 APIs) | HaoNN
4 | Add Login User, Admin (3 APIs) | HaoNN
5 | Draw Package diagram of Back-end | HaoNN
6 | Add MasUser Functions (8 APIs) | NhanNT
7 | Add Question Functions (5 APIs) | NhanNT
8 | Implement manage account on frontend web admin | HungVQ
9 | Write function requirement for SRS document (Manage major, manage subjects, manage account) | HungVQ
10 | Draw UI prototype for web user on Figma | HuyNH
11 | Draw UI prototype for web admin on Figma | HuyNH
12 | Create UI for web admin | HuyNH
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | No table for register mentor and register more subject for mentor | In Progress | Add one table for registration data
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Write document SRS section II, Write Design document Package Description
2 | Code
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A | N/A | N/A | N/A

## Week 05
PROJECT REPORT
Group | Group 01 - Mentor Appointment Scheduling Application
Week | 06/06/2022 - 10/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Write document SRS section II, Write Design document | In Progress
2 | Coding | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Write package description of backend | HaoNN
2 | Implement Slot API in backend (4 APIs) | HaoNN
3 | Implement Appointment API in backend (10 APIs) | HaoNN
4 | Update screen UI for web user | HuyNH
5 | Update screen UI for web admin | HuyNH
6 | Implement repository & service for Rating API | NhanNT
7 | Modify API MasUser logic code | NhanNT
8 | Write functional requirements for SRS document( Manage register requests | HungVQ
9 | Code front end for admin and user application | HungVQ
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
N/A | N/A | In Progress | N/A
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Write document SRS section II | 2022-06-17
2 | Write Design document Database Schema | 2022-06-14
3 | Coding
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A | N/A | N/A | N/A

## Week 06
PROJECT REPORT
Group | Group 01 - Mentor Appointment Scheduling Application
Week | 13/06/2022 - 17/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Write document SRS section II, Write Design document | In Progress
2 | Code | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Write document SRS section II | All Member
2 | Write Design document Database Schema | HaoNN
3 | Modify Entities, Models (Add IsActive attribute in to each entities) | HaoNN
4 | Modify API Subject, Major, MentorSubject, Slot, Appointment Repository logic code | HaoNN, NhanNT
5 | Implement Rating API in backend (5 APIs) | NhanNT
6 | Write functional requirements for SRS document( Manage register requests | HungVQ
7 | Code front end for admin and user application | HungVQ
8 | Code front end for admin and user application | HuyNH2
9 | Design and update wireframe for website | HuyNH2
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
N/A | N/A | In Progress | N/A
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Write Design document: Database Tables | 2022-06-21
2 | Write document SRS section II | 2022-06-24
3 | Coding
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A | N/A | N/A | N/A

## Week 07
PROJECT REPORT
Group | Group 01 - Mentor Appointment Scheduling Application
Week | 20/06/2022 - 24/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Write Design document: Database Tables | In Progress
2 | Write document SRS section II | In Progress
3 | Coding | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Write Design document: Database Tables | HaoNN
2 | Modify, fix code in all Back-end | HaoNN, NhanNT
3 | Write Design document: Class Diagram (Major) | HaoNN, NhanNT
4 | Write functional requirements for SRS document( Manage register requests | HungVQ
5 | Code front end for admin and user application | HungVQ
6 | Code front end for admin and user application | HuyNH2
7 | Write requirement for SRS document | HuyNH2
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
N/A | N/A | In Progress | N/A
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Coding
2 | Complete Document SRS and Design | 2022-07-01
3
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A | N/A | N/A | N/A

## Week 08
PROJECT REPORT
Group | Group 01 - Mentor Appointment Scheduling Application
Week | 27/06/2022 - 01/07/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Complete Document Design | In Progress
2 | Complete Document SRS section II | In Progress
3 | Coding | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Draw Subject, Slot, Appointment, MentorSubject Features class diagram | HaoNN
2 | Update, fix code backend | HaoNN, NhanNT
3 | Draw MasUser, Question, Rating Features class diagram | NhanNT
4 | Write functional requirements for SRS document( Manage register requests | HungVQ
5 | Code front end for admin and user application | HungVQ
6 | Code front end for admin and user application | HuyNH2
7 | Update requirements for SRS document | HuyNH2
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
N/A | N/A | In Progress | N/A
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Coding
2 | Complete Document SRS and Design | 2022-07-15
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A | N/A | N/A | N/A

## Week 09
PROJECT REPORT
Group | Group 01 - Mentor Appointment Scheduling Application
Week | 11/07/2022 - 15/07/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Complete Document Design | In Progress
2 | Complete Document SRS section II | In Progress
3 | Coding | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Update , fix code back-end | HaoNN, NhanNT
2 | Test font-end | All members
3 | Update , fix code font-end | HuyNH2, HungVQ
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
N/A | N/A | In Progress | N/A
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
N/A | N/A | N/A | N/A
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A | N/A | N/A | N/A